## 20120421
| content | design | prog / mgmt | amplex time
a |  | 8 |  |  | 10 | design?
a |  |  | 2 | ? | 2 | setup project
a |  |  | 3 | ? | 6 | implement featured items
a |  |  | 0.5 | 2012-01-29 | 2 | main menu navigation
a |  |  |  | 2012-01-30 | 2 | main menu navigation
a |  |  | 0.5 | 2012-01-31 | 2 | complete menu, start adding main pov
a |  | 1 |  | 2012-02-07 | 3 | pov / button styling
a |  |  | 0.5 | 2012-02-10 | 1.5 | setup search
a |  |  |  | 2012-02-11 | 4 | featured items programming
a |  |  | 1.5 | 2012-02-12 | 2 | pdf setup
a |  | 1 | 1 | 2012-02-20 | 2 | design -> dev handoff
a |  |  | 2 | 2012-02-21 | 4 | implement header, nav, search, hp cut
a |  | 0.5 |  | 2012-02-22 | 2 | hp news styling
a |  | 0.5 |  | 2012-02-23 | 2.5 | featured items styling
a |  |  | 2 | 2012-02-24 | 4 | sub page setup
a |  |  |  | 2012-02-25 | 3 | more subpage setup
a |  |  |  | 2012-02-26 | 3 | featured item template setup, m/d setup for news / featured items, dev site setup
a |  |  |  | 2012-03-09 | 2 | search
a |  |  |  | 2012-03-10 | 2 | search
a |  |  |  | 2012-03-12 | 1 | admin, respond to email from amy,
a |  |  | 0.5 | 2012-03-12 | 1 | search results styling, push to dev
a |  |  | 1 | 2012-03-15 | 0.5 | prep assoc logos
a |  |  | 0.25 |  | 0.25 | move search
a |  |  | 0 | 2012-03-16 | 2 | fix bug where unable to select image in tiny mce
a |  |  | 0.5 | 2012-03-17 | 2 | search images / styling
a |  |  |  | 2012-03-18 | 4 | featured items setup, correct insertion order, template setup / styling
a | 0.25 |  |  | 2012-03-19 | 0.25 | about us content
a | 0.5 |  |  |  | 0.5 | faq content
a |  |  |  |  | 2 | push changes for featured items to dev
a |  |  |  | 2012-03-25 | 2 | style navigation
a |  |  | 0.5 | 2012-03-26 | 1 | update pdf doc, update text in registration page
a |  |  |  |  | 0.25 | implement main nav hover styles
a |  |  | 3.75 | 2012-04-07 | 6 | florida map (cumulative)
a |  |  | 3.75 | 2012-04-15 | 2 | us map (cumulative)
| 0.75 | 11 | 15.75 |  | 75.75
| 35 | 55 | 55
| 26.25 | 605 | 866.25
Note on C3: Jerry Woodlock: lr
Note on C13: Jerry Woodlock: lr

## 20120630
content | design | prog / mgmt |  | amplex time
[5 empty] | content | dev
|  |  | x | 2012-04-22 |  | 0.75 | 0.75 | us map, add cities
|  |  | x | 2012-04-22 |  | 0.25 | 0.25 | product highlights
|  |  | x | 2012-04-22 |  | 0.25 | 0.25 | product highlights
|  |  | x | 2012-04-22 |  | 1.5 | 1.5 | add slide content, style text/buttons
|  |  | x | 2012-04-22 |  | 2 | 2 | update content to include links, style for links, embedded li, ie7 fix for alignment, mod js to pause on hover
|  |  | x | 2012-04-22 |  | 0.5 | 0.5 | sage contact / research
|  |  | x | 2012-04-22 |  | 0.5 | 0.5 | update module text / links, change delivery -> freight in paths, text, and in .js fles for maps
|  |  | x | 2012-04-22 |  | 0.25 | 0.25 | slide text updates / move slides
|  |  | x | 2012-05-23 |  | 1.5 | 2 | meet w/amy, tami, george, steven to discuss updates, photos
|  |  | x | 2012-05-25 |  | 0.25 | 0.25 | ph, w/tami discuss prev meeting, catalog, sage, etc
|  |  | x | 2012-05-26 |  | 2 | 2 | parts catalog data implementation
|  |  | x | 2012-05-27 |  | 4.5 | 4.5 | parts catalog import processing, parts export service
|  |  | x | 2012-05-28 |  | 4 | 4 | parts export / import
|  |  | x | 2012-05-29 |  | 2 | 2 | parts + pricing export /import
|  |  | x | 2012-05-30 |  | 1.5 | 1.5 | parts export
|  |  |  | 2012-06-01 |  |  | 1 | parts search
|  |  |  | 2012-06-02 |  |  | 2 | parts search
|  |  |  | 2012-06-03 |  |  | 4 | parts search
|  |  | x | 2012-06-04 |  | 1.5 | 2 | meet w/tami, test sage export on site
|  |  | x | 2012-06-04 |  | 1 | 2 | parts export, adjusted
|  |  | x | 2012-06-05 |  | 1 | 2 | parts import, adjusted
|  |  | x | 2012-06-08 |  | 2 | 2 | parts search / display
|  |  | x | 2012-06-08 |  | 4.75 | 5 | parts display, catalog display
|  |  | x | 2012-06-21 |  | 0.5 | 0.5 | parts catalog /thumbnails
|  |  | x | 2012-06-22 |  | 3.75 | 4 | parts catalog, search updates, show thumbnails, catalog styling, filter data imports for 'do not use/sell', thumbnails in global search, vpn setup test
|  |  | x | 2012-06-23 |  | 4.5 | 5 | style search input, complete show thumbnails in cat and general search, complete import filter, hide zero prices, complete search back behavior, style search results
|  |  | x | 2012-06-24 |  | 4.75 | 5 | update social links, add zone hardiness, update us map, add request a quote form, ad load quantities
|  |  | x | 2012-06-26 |  | 0.5 | 0.5 | assist w/youtube
|  |  |  | 2012-06-27 |  | 0 | 1 | prod site setup
|  |  | x | 2012-06-28 |  | 0.25 | 0.25 | ph call, prep images for danielle
|  |  | x | 2012-06-28 |  | 0.25 | 0.25 | review danielle's work, request some updates
|  |  | x | 2012-06-29 |  | 1.75 | 2 | setup discount asp server, modify the upload task to not timeout, vpn setup attempt
|  |  |  | 2012-06-30 |  | 0 | 0.25 | vpn setup
0 | 0 | 0 |  |  | 0 | 48.25 | 61
35 | 55 | 55
0 | 0 | 0

## 20120903
content | design | prog / mgmt | amplex time
|  |  |  | content | dev
|  |  | 2012-07-01 |  | 1 | 1.5 | setup of content updates to request form, add price disclaimers, salesmen
|  |  | 2012-07-01 |  | 0.25 | 0.25 | review danielle's email re updates
|  |  | 2012-07-21 |  | 0.5 | 0.5 | research sage business works install issue
|  |  | 2012-08-06 |  | 1.5 | 1.5 | staff page, update pictures
|  |  | 2012-08-07 |  | 2 | 2 | staff page, update pictures, layout page
|  |  | 2012-08-10 |  | 1 | 2 | ticker, cutup images
|  |  | 2012-08-11 |  | 4 | 4 | ticker, implementation
|  |  | 2012-08-12 |  | 1 | 1 | ticker, release, setup
|  |  | 2012-08-13 |  | 1 | 2 | ticker admin
|  |  | 2012-08-15 |  | 1 | 2 | ticker admin
|  |  | 2012-08-16 |  | 1 | 2 | ticker admin
|  |  | 2012-08-18 |  | 2 | 3 | ticker admin / push
|  |  | 2012-08-19 |  | 4 | 4 | slideshow implement new styles, cut/clean images
|  |  | 2012-08-20 |  | 2 | 2 | touchup slideshow image, push slideshow, setup, qr code research
|  |  | 2012-08-28 |  | 1.75 | 1.75 | staff updates
|  |  | 2012-09-02 |  | 0.25 | 0.5 | staff update
24.25
0 | 0 | 0 |  | 0 | 48.5 | 30
35 | 55 | 55
0 | 0 | 0

## account
date | in | out | description
2012-05-07 | 797.75 |  | amplex, invoice 4/21/12
2012-05-11 |  | 100 | lawrence, design, 2 hours for design->dev handoff
2012-05-14 |  | 150 | danielle torres
2012-07-06 |  | 100 | danielle torres
2012-07-17 |  | 250 | danielle torres
2012-07-29 | 2803.75 |  | amplex, invoice 6/30/12
2012-06-27 |  | 180 | hosting
2012-09-27 |  | 15 | domain name change

## 20121017
content | design | prog / mgmt | amplex time
|  |  |  | content | dev
|  |  | 2012-09-06 |  | 2 | 2 | various changes, add faustino, remove links, modify slideshow buttons, behaviour
|  |  | 2012-09-07 |  | 2 | 2 | various changes, add external links to ticker admin
|  |  | 2012-09-14 |  | 1 | 1 | research sage install, prepare instructions for featured items
|  |  | 2012-09-20 |  | 1 | 1 | sage export setup / testing
|  |  | 2012-09-21 |  | 2 | 2 | sage export setup / testing
|  |  | 2012-09-21 |  | 0.25 | 0.25 | how to create a new user doc
|  |  | 2012-09-24 |  | 0.75 | 0.75 | added location pages, updated footer links
|  |  | 2012-09-26 |  | 0.25 | 0.25 | review emails, change requests
|  |  | 2012-09-27 |  | 1 | 1 | training w/amy
|  |  | 2012-09-27 |  | 0.25 | 0.25 | hosting setup
|  |  | 2012-09-27 |  | 2 | 2 | style updates, minor speed changes
|  |  | 2012-09-28 |  | 2 | 2 | final updates
|  |  | 2012-09-29 |  | 2 | 4 | add conditional form recipient logic
|  |  | 2012-10-01 |  | 0.25 | 0.25 | research dns change
|  |  | 2012-10-01 |  | 2 | 2 | add form, update slide speed, setup dns
|  |  | 2012-10-02 |  | 0.25 | 0.25 | link updates, add google analytics code
|  |  | 2012-10-04 |  | 1 | 1 | facebook commenting setup, discussions re commenting, become a vendor
|  |  | 2012-10-05 |  | 0.5 | 0.5 | update comments form, research featured item upload, reduce items in ticker
|  |  | 2012-10-06 |  | 2 | 2 | add become a vendor button, setup webmaster tools
|  |  | 2012-10-08 |  | 3 | 3 | add send welcome email
|  |  | 2012-10-13 |  | 1.5 | 1.5 | update cta buttons to fit in left side
|  |  | 2012-10-13 |  | 2 | 6 | update ticker to support many items
[5 empty] | 29 | 1595
[5 empty] | 120 |  | hosting 9/27 - 12/27

## 20121128
content | design | prog / mgmt | amplex time
|  |  |  | content | dev
|  |  | 2012-10-17 |  | 1 | 1 | meet onsite
|  |  | 2012-10-17 |  | 1 | 1 | training w/amy
|  |  | 2012-10-18 |  | 1 | 1 | mobile switching
|  |  | 2012-10-21 |  | 1.5 | 1.5 | slideshow styling / setup, staff styling
|  |  | 2012-10-29 |  | 0.5 | 3 | complete mobile switching, test, add to amplex, disbable script for mobile
|  |  | 2012-10-30 |  | 2.75 | 3 | setup location slideshows
|  |  | 2012-10-31 |  | 1 | 1 | setup location slideshows
|  |  | 2012-11-05 |  | 0.25 | 0.25 | comms / research re ordering items
|  |  | 2012-11-08 |  | 1.25 | 1.25 | research sage re ordering items
|  |  | 2012-11-14 |  | 0.5 | 0.5 | setup plant type / size type in sage, provide instructions
2012-11-16
2012-11-17
|  |  | 2012-11-18 |  | 0 | 1 | plant type / size export /import processing
|  |  | 2012-11-19 |  | 0 | 1 | plant type / size export /import processing
|  |  | 2012-11-20 |  | 2 | 2 | plant type / size export /import processing
|  |  | 2012-11-21 |  | 0 | 1 | plant type config
|  |  | 2012-11-25 |  | 1 | 1 | plant type config
|  |  | 2012-11-26 |  | 2 | 2 | plant type config / push results / prep doc

## 20130126
content | design | prog / mgmt | amplex time
|  |  |  | content | dev
|  |  | 2012-12-16 |  | 0.25 | 0.25 | review email re job application form
|  |  | 2013-01-01 |  | 3 | 5 | replicate job application
|  |  | 2013-01-06 |  | 3 | 3 | combine forms, populate form fields, update website
[5 empty] | 120 |  | hosting 12/28 - 3/27

## 20130401
actual | billed
0.5 | 0.5 | 2013-01-29 | re email, seo, mobile website
1.75 | 1.75 | 2013-02-11 | meeting on site, re price list, analytics, catalog organization
2 | 1.75 | 2013-02-19 | research doc management solutions
3 | 2.75 | 2013-03-06 | mobile site upgrade, header creation
0.25 | 0.25 | 2013-03-08 | investigate / allocate space to featured items
1.5 | 1.5 | 2013-03-11 | mobile site header updates, configure phone, add social media icons, background
1.5 | 1.5 | 2013-03-15 | mobile site, theme rollin, buttons
2 | 2 | 2013-03-16 | mobile footer, featured comp
2 | 1.75 | 2013-03-17 | package, test setup
0.5 | 0.5 | 2013-03-18 | mobile site, login, correct footer color, add freight link
0.25 | 0.25 | 2013-03-18 | research image name issue, add letter folders for plant images
0.5 | 0.5 | 2013-03-19 | move images into folders, update cat items, featured items
2.25 | 2.25 | 2013-03-19 | style main nav bar, configure redirection, style login, style contact us
1 | 1 | 2013-03-20 | locations
1.75 | 1.75 | 2013-03-22 | added static location map, styled featured item slide
4.25 | 4.25 | 2013-03-23 | implement slideshow, reduce image sizes
1.25 | 1.25 | 2013-03-28 | featured items form, populate main site + mobile site
4.75 | 3.25 | 2013-03-29 | style featured items template, list page, implement on home page
1.5 | 1.25 | 2013-03-30 | dev push / setup
30

## 20130603
actual | billed
2.25 | 2.25 | 2013-05-14 | updates for minimal nav, admin, mobile featured submission, prep release
1.75 | 1.75 | 2013-05-15 | initial mobile setup
0.75 | 0.75 | 2013-05-18 | mobile setup
0.5 | 0.5 | 2013-05-20 | mobile dns setup
2 | 2 | 2013-05-22 | mobile site final setup, analytics install, email details
7.25

## 20130811
actual | billed
0.5 | 0.5 | 2013-08-11 | setup cross domain login
0.5
#NAME?

## Hosting
hosting
| invoice | date range
| 20130126 | hosting 12/28 - 3/27
| 2013-04-03 | 3/28 - 6/27
| 2013-09-07 | 6/28 - 9/27
| 2014-01-17 | 9/28 - 3/27
| 2014-05-06 | 3/28 - 6/27
| 2014-07-04 | 6/28 - 9/27
| 2014-12-27 | 9/28 - 12/27
| 2015-03-01 | 12/28 - 3/27
| 2015-05-10 | 3/28 - 6/27
| 2015-07-03 | 6/28-9/27
| 2015-11-06 | 9/28 - 12/27
| 2016-01-11 | 12/28/15 - 3/27/16
| 2016-05-02 | 3/28-6/27
| 2016-06-28 | 6/28/16-9/27/16

## noclude
2015-03-30 | 0.25 | staff images
2015-03-31 | 0.25 | staff images
2015-04-02 | 0.25 | staff images
another | 0.25 | staff images
2015-07-03 | 0.25 | trademark text research
2015-07-07 | 1 | update main header, upload
2015-07-07 | 1 | update mobile header/footer, main article talent for the trade

## 20190820
2019-08-20 | 0.5 | add hubspot code
2019-08-25 | 0.25 | modify sales form
2020-02-19 | 0.25 | backup db, export users into excel
before 3/7 | 0.75 | meet at amplex
2020-03-07 | 1 | some initial changes, style,